## 1. Product Overview
Item | Description
Product Name | AI-Powered SEO & AEO Optimization Agent
Product Vision/ Purpose | To automate website optimization by improving both search ranking (SEO) and AI-based answer visibility (AEO) using AI-driven analysis and content improvement.
Business Goals / Key Success factors | Improve website visibility on search engines and AI platforms Reduce manual SEO effort through automation Provide real-time insights and optimization suggestions Increase website traffic and user engagement Help businesses generate more leads, conversions, and profit
Primary Stakeholders | Business owners / Website owners Digital marketers Content creators HR / Managers (for decision making)

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up with email and OTP so that I can access my account securely. | Registration screen details | Won't Have | 5 | To Do | Backend Dev team names | Can be a link to document | names
Pop Ups once registered
Login screen
OTP Generation
Sending OTP
Login Error Screen
| Website Analysis | US2 | As a user, I want to enter a website URL so that I can analyze it. | URL input field | Must Have | 8 | In Progress | Frontend Dev | Test URL input and API response | QA Team
API call to backend
| Content Optimization | US7 | As a user, I want improved content so that I can increase visibility. | FAQ generation | Could Have | 13 | To Do | AI Team | Check generated content | QA Team
Content rewriting
E2 | Dashboard | US5 | As a user, I want to view analytics on a dashboard so that I can see trends quickly. | Dashboard UI | Should Have | 13 | In Progress | Frontend Dev | Test dashboard UI and data display | QA Team
Charts
Score display
| Suggestions Engine | US6 | As a user, I want suggestions so that I can improve my website. | AI suggestions | Could Have | 8 | In Progress | AI Team | Test suggestions accuracy | QA Team
Issue detection
| SEO & AEO Analysis | US3 | As a user, I want to get SEO and AEO scores so that I can understand performance. | Firecrawl scraping | Must Have | 13 | In Progress | Backend + AI Team | Validate score generation | QA Team
Gemini AI analysis
Score generation
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2025-11-15 | Authentication, Dashboard MVP | None | On Track
v0.2 | 2025-11-22 | Website Analysis, SEO Score Generation | Firecrawl + AI API integrationOn Track | Planned
v0.3 | 2025-11-29 | AEO Analysis, Suggestions Engine | AI Model (Gemini) integration | Planned
v0.4 | 2025-12-06 | Content Optimization (FAQ generation, structured answers) | AI content generation | Planned
v0.5 | 2025-12-13 | Dashboard UI Improvements, Score Visualization | Frontend UI components | Planned
v1.0 | 2025-12-20 | One-Click Optimization, Full System Integration | Backend + Frontend integration | Planned
v1.1 | 2025-12-27 | Automated Content Update (GitHub/API Integration) | GitHub API | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Team collaboration was great | Test coverage was low | Automate test pipeline in next sprint | Test Lead